## Site Performance Report
Section | Key Metric | Value / Detail | Status | Key Decision Item
Overview Metrics | Total Booking Value Achievement | 20.1% Achieved | Needs Review | Establish Q1 promotional campaigns & broker schemes.
Overview Metrics | Collections Target Achievement | 2.8% Achieved | Critically Delayed | Escalate dunning notices for bills overdue >30 days.
Overview Metrics | Construction CoC Target Achievement | 23,346,703 Spent vs Target 53,500,000 | On Track | Maintain progress while tracking raw material cost trends.
Net Cash Flow | Variance vs AOP Target | Underperforming target by -255,159,703 INR | Deficit Risk | Utilize backup credit facility or delay non-critical project expenditures.

## Cash Flow Report
Metric | Actual Inflow | Collections Due / Overdue | Actual Outflow CoC | Other Costs | Actual NCF | Target NCF | Variance vs Target | Top Cash-flow Risks
Net Cash Flow | 18187000 | 15424000 | 23346703 | 92000000 | -97159703 | 158000000 | -255159703 | Unpaid complete milestones: None

## Progress Update
Category | Metric | Actual | Target | Variance | Status/Achievement
Sales | Booking Value | 227818000 | 1133500000 | -905682000 | 20.1% Achieved
Sales | 1BHK Units Sold | 3 | 28 | -25 | 3 vs Target 28
Sales | 2BHK Units Sold | 5 | 52 | -47 | 5 vs Target 52
Sales | 3BHK Units Sold | 5 | 21 | -16 | 5 vs Target 21
Collections | Total Collections | 18187000 | 660000000 | -641813000 | 2.8% Achieved
Construction | Construction Cost | 23346703 | 53500000 | 30153297 | 23,346,703 Spent vs Target 53,500,000

## Escalation Summary
Project | Item | Metric Impacted | Reason | Suggested Owner | Required Action | Due Date | Severity
Aster Grove Residences | Sales Risk | Booking Value | Actual (227,818,000) is < 80% of Target (1,133,500,000) (Achievement: 20.1%) | Rohan Mehta | Prepare sales recovery and incentive pipeline plan | Immediate | Red
Aster Grove Residences | Product Mix Risk | Unit Sales Mix | Shortfall in units sold for configs: 1BHK, 2BHK, 3BHK | Rohan Mehta | Review pricing Strategy or offer targeted schemes for lagging configurations | Next 7 Days | Amber
Aster Grove Residences | Collections Risk | Total Collections | Actual (18,187,000) is < 85% of Target (660,000,000) (Achievement: 2.8%) | Collections Head | Initiate intensive customer reminders and follow-ups | Immediate | Red
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Sara Chopra is overdue by 47.0 days | Kunal Shah | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Aarush Mathur is overdue by 33.0 days | Priya Menon | Direct demand follow up for overdue invoice of 384,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Aarush Mathur is overdue by 59.0 days | Rohan Iyer | Direct demand follow up for overdue invoice of 1,152,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Samar Menon is overdue by 59.0 days | Meera Nair | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Advik Kapadia is overdue by 41.0 days | Tanvi Rao | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Kiara Kapoor is overdue by 51.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 2,670,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Aarush Talwar is overdue by 60.0 days | Meera Nair | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Aarush Talwar is overdue by 32.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 1,947,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Tara Bedi is overdue by 34.0 days | Tanvi Rao | Direct demand follow up for overdue invoice of 305,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Tara Bedi is overdue by 47.0 days | Kunal Shah | Direct demand follow up for overdue invoice of 1,097,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Misha Walia is overdue by 41.0 days | Tanvi Rao | Direct demand follow up for overdue invoice of 446,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Misha Walia is overdue by 32.0 days | Tanvi Rao | Direct demand follow up for overdue invoice of 446,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Naina Kapoor is overdue by 39.0 days | Priya Menon | Direct demand follow up for overdue invoice of 260,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Anika Balan is overdue by 59.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 986,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Sara Chopra is overdue by 34.0 days | Rohan Iyer | Direct demand follow up for overdue invoice of 588,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Pihu Mehra is overdue by 59.0 days | Priya Menon | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Anika Chawla is overdue by 31.0 days | Meera Nair | Direct demand follow up for overdue invoice of 598,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Yash Kapoor is overdue by 39.0 days | Tanvi Rao | Direct demand follow up for overdue invoice of 1,157,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Aisha Kapoor is overdue by 60.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Aisha Kapoor is overdue by 50.0 days | Rohan Iyer | Direct demand follow up for overdue invoice of 419,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Sara Balan is overdue by 58.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Sara Balan is overdue by 32.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 660,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Misha Gill is overdue by 38.0 days | Ankit Suri | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Misha Gill is overdue by 42.0 days | Priya Menon | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Avni Mathur is overdue by 59.0 days | Meera Nair | Direct demand follow up for overdue invoice of 866,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Avni Mathur is overdue by 38.0 days | Rohan Iyer | Direct demand follow up for overdue invoice of 1,443,000 INR | Next 48 Hours | Amber
Aster Grove Residences | Collection Priority | Overdue customer billing milestone | Customer Dev Menon is overdue by 58.0 days | Priya Menon | Direct demand follow up for overdue invoice of 0 INR | Next 48 Hours | Amber
Eden Square | Construction Delay Risk | Milestone Progress | Activity 'Window frame' delayed by 25 days due to: Material delay | Prakash Pawar | Deploy extra labor forces to expedite construction process | Immediate | Red
Eden Square | Construction Delay Risk | Milestone Progress | Activity 'Window frame' delayed by 25 days due to: nan | Nilesh More | Deploy extra labor forces to expedite construction process | Immediate | Red
Eden Square | Cross-functional escalation | Project Viability / NCF | Coinciding Sales Risk with critical Collections / Construction milestones delay. | Project Head | Convene emergency review board meeting to align cross-functional targets | Immediate | Red

## Action Plan
Owner | Department | Task | Priority | Due Date
Rohan Mehta | Sales | Formulate and deploy marketing campaign for BHK configurations with low sales velocity | High | Immediate
Rohan Mehta | Sales | Re-evaluate customer positioning and broker brokerage rates for: 1BHK, 2BHK, 3BHK | Medium | Next 7 Days
Collections Head | Collections | Formulate and deploy collection camps and coordinate broker mediation | High | Immediate
Prakash Pawar | Construction | Expedite delayed activity: 'Window frame' (Currently delayed by 25 days) | High | Next 7 Days
Nilesh More | Construction | Expedite delayed activity: 'Window frame' (Currently delayed by 25 days) | High | Next 7 Days

## Data Quality Report
Timestamp | File | Field/Activity | Issue Type | Details
2026-06-29 20:42:11 | Construction file | Window frame | Clarification Required | Activity delayed by 25 days but 'Delay Reason' is missing.
2026-06-29 20:42:11 | Collections Tracker | Agreement | Milestone Mismatch | Milestone Linked 'Agreement' in Collections does not match any Activity in Construction Daily targets.
2026-06-29 20:42:11 | Collections Tracker | Finishing Completion | Milestone Mismatch | Milestone Linked 'Finishing Completion' in Collections does not match any Activity in Construction Daily targets.
2026-06-29 20:42:11 | Collections Tracker | Booking | Milestone Mismatch | Milestone Linked 'Booking' in Collections does not match any Activity in Construction Daily targets.
2026-06-29 20:42:11 | Collections Tracker | Possession | Milestone Mismatch | Milestone Linked 'Possession' in Collections does not match any Activity in Construction Daily targets.
2026-06-29 20:42:11 | System Rules | System | Cross checks Validation Error | 'Customer Code'

## Draft Communications
Recipient | Channel | Message
Rohan Mehta | Teams / Email | Urgent Action Required: Q1 actual booking value (227,818,000 INR) is underperforming vs targets (1,133,500,000 INR). Please draft a configuration-wise action plan.
Kunal Shah | Teams / Email | Follow-up Alert: Customer Sara Chopra is currently 47.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Priya Menon | Teams / Email | Follow-up Alert: Customer Aarush Mathur is currently 33.0 days overdue with outstanding amount of 384,000 INR. Please issue formal dunning notice.
Rohan Iyer | Teams / Email | Follow-up Alert: Customer Aarush Mathur is currently 59.0 days overdue with outstanding amount of 1,152,000 INR. Please issue formal dunning notice.
Meera Nair | Teams / Email | Follow-up Alert: Customer Samar Menon is currently 59.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Tanvi Rao | Teams / Email | Follow-up Alert: Customer Advik Kapadia is currently 41.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Kiara Kapoor is currently 51.0 days overdue with outstanding amount of 2,670,000 INR. Please issue formal dunning notice.
Meera Nair | Teams / Email | Follow-up Alert: Customer Aarush Talwar is currently 60.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Aarush Talwar is currently 32.0 days overdue with outstanding amount of 1,947,000 INR. Please issue formal dunning notice.
Tanvi Rao | Teams / Email | Follow-up Alert: Customer Tara Bedi is currently 34.0 days overdue with outstanding amount of 305,000 INR. Please issue formal dunning notice.
Kunal Shah | Teams / Email | Follow-up Alert: Customer Tara Bedi is currently 47.0 days overdue with outstanding amount of 1,097,000 INR. Please issue formal dunning notice.
Tanvi Rao | Teams / Email | Follow-up Alert: Customer Misha Walia is currently 41.0 days overdue with outstanding amount of 446,000 INR. Please issue formal dunning notice.
Tanvi Rao | Teams / Email | Follow-up Alert: Customer Misha Walia is currently 32.0 days overdue with outstanding amount of 446,000 INR. Please issue formal dunning notice.
Priya Menon | Teams / Email | Follow-up Alert: Customer Naina Kapoor is currently 39.0 days overdue with outstanding amount of 260,000 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Anika Balan is currently 59.0 days overdue with outstanding amount of 986,000 INR. Please issue formal dunning notice.
Rohan Iyer | Teams / Email | Follow-up Alert: Customer Sara Chopra is currently 34.0 days overdue with outstanding amount of 588,000 INR. Please issue formal dunning notice.
Priya Menon | Teams / Email | Follow-up Alert: Customer Pihu Mehra is currently 59.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Meera Nair | Teams / Email | Follow-up Alert: Customer Anika Chawla is currently 31.0 days overdue with outstanding amount of 598,000 INR. Please issue formal dunning notice.
Tanvi Rao | Teams / Email | Follow-up Alert: Customer Yash Kapoor is currently 39.0 days overdue with outstanding amount of 1,157,000 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Aisha Kapoor is currently 60.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Rohan Iyer | Teams / Email | Follow-up Alert: Customer Aisha Kapoor is currently 50.0 days overdue with outstanding amount of 419,000 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Sara Balan is currently 58.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Sara Balan is currently 32.0 days overdue with outstanding amount of 660,000 INR. Please issue formal dunning notice.
Ankit Suri | Teams / Email | Follow-up Alert: Customer Misha Gill is currently 38.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Priya Menon | Teams / Email | Follow-up Alert: Customer Misha Gill is currently 42.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.
Meera Nair | Teams / Email | Follow-up Alert: Customer Avni Mathur is currently 59.0 days overdue with outstanding amount of 866,000 INR. Please issue formal dunning notice.
Rohan Iyer | Teams / Email | Follow-up Alert: Customer Avni Mathur is currently 38.0 days overdue with outstanding amount of 1,443,000 INR. Please issue formal dunning notice.
Priya Menon | Teams / Email | Follow-up Alert: Customer Dev Menon is currently 58.0 days overdue with outstanding amount of 0 INR. Please issue formal dunning notice.